## Summary
SpringHRM Menu & Pages | Design Status | Date to Complete | Notes | Development Complete
● Admin Dashboard | Design Not Complete | Not Started
● Manager Dashboard | Design Not Complete | Not Started
● Employee (Non Manager) Dashboard | Design Not Complete | Not Started
● Spring Admin | Complete | Not Started
− User Management | Complete | Not Started
└ Users | Complete | Not Started
└ User Roles | Complete | Not Started
- Setup SpringTools | Complete | Not Started
└ Dashboard Settings | Missing | Not Started | See dashboard design
└ Email Settings | Complete | Not Started
└ Email Subscription | Complete | Not Started
└ Localization | Complete | Not Started
└ Notifications | Complete | Not Started
└ Open ID | Complete | Not Started
└ Authentication | Complete | Not Started
└ LDAP | Complete | Not Started
- API Settings | Complete | Not Started
− Audit Trail | Complete | Not Started
− Auditing | Complete | Not Started
− Backups | Complete | Not Started
− Delete Account | Complete | Not Started
− Settings | Complete | Not Started
└ Social Settings | Complete | Not Started
└ Social Site Settings | Not Correct | Not Started | See Hip Chat for functionality
└ Security Settings | Complete | Not Started
− Manage My Account | Need to Update | Not Started | Please update Edit Subscription page
● Core HR | Complete | Not Started
− Setup Org Data | Complete | Not Started
└ General Information | Complete | Not Started
└ Location | Complete | Not Started
└ Department Structure | Complete | Not Started
└ Reporting Method | Complete | Not Started
└ Define Setup Hierarchy | Complete | Not Started
└ View Org Chart | Complete | Not Started
− Setup CoreHR | Complete | Not Started
└ Optional Fields | Complete | Not Started
└ Custom Fields | Complete | Not Started
└ Data Import | Complete | Not Started
└ Termination Reasons | Complete | Not Started
− Setup Job Data | Complete | Not Started
└ Job Titles | Complete | Not Started
└ Salary Components | Complete | Not Started
└ Pay Grades | Complete | Not Started
└ Employment Status | Complete | Not Started
└ Job Categories | Complete | Not Started
└ Work Shifts | Complete | Not Started
− Setup Credentials | Complete | Not Started
└ Skills | Complete | Not Started
└ Licenses | Complete | Not Started
└ Education | Complete | Not Started
└ Languages | Complete | Not Started
└ Memberships | Complete | Not Started
− Setup Nationalities | Complete | Not Started
− Setup News & Documents | Complete | Not Started
└ News | Complete | Not Started
└ News Categories | Complete | Not Started
└ Documents | Complete | Not Started
└ Document Categories | Complete | Not Started
└ Events | Complete | Not Started
− Set up Onboarding | Complete | Not Started
└ Task Types | Complete | Not Started
└ Events | Complete | Not Started
− Assets Setup Equipment | Complete | Not Started
└ Asset Brand Information | Complete | Not Started
└ Asset Categories | Complete | Not Started
└ View Assets Equipment Assignment | Complete | Not Started
└ Vendors | Complete | Not Started
● HR Reports | Complete | Not Started
− Onboarding Reports | Complete | Not Started
└ Event Progress | Complete | Not Started
└ Participant Progress | Complete | Not Started
− Employee Reports | Complete | Not Started
└ Employee Report | Complete | Not Started
└ Head Count Report | Complete | Not Started
└ License Expiration Report | Complete | Not Started
└ Employee Turnover Hiring Report | Complete | Not Started
└ Employee Turnover Termination Report | Complete | Not Started
Employee diversity report | Complete | Not Started
Employee custom fields | Complete | Not Started
└ Employee Date of Birth | Complete | Not Started
└ Employee Employees hired for each location | Complete | Not Started
└ Employee Employees hired for each sub-unit | Complete | Not Started
└ Employee Employees over 20 years | Complete | Not Started
└ Employee Employment Status of Employees | Complete | Not Started
└ Female Employee List with Service period over 1 year | Complete | Not Started
└ Employee Joined Date between 2010 - 2012 | Complete | Not Started
└ Employee Marital Status | Complete | Not Started
└ Employee PIM data verification | Complete | Not Started
└ Employee PIM Sample Report | Complete | Not Started
└ Employee Supervisor Subordinate Details | Complete | Not Started
− Management Reports | Complete | Not Started
Employee job history report | Complete | Not Started
New hires report | Complete | Not Started
Employee Termination date | Complete | Not Started
Employee list report | Complete | Not Started
Employee contact list report | Complete | Not Started
Employee emergency contact report | Complete | Not Started
Employee timesheet report | Complete | Not Started
Employee length of service report | Complete | Not Started
Employee work contact report | Complete | Not Started
Employee start date | Complete | Not Started
Mandatory documents | Complete | Not Started
− Performance Reports | Complete | Not Started
- Appraisal summary report | Complete | Not Started
Review and Appraisal Progress report | Complete | Not Started
Performance Comparison Report | Complete | Not Started
Employee Performance Profile | Complete | Not Started
Performance Progress | Complete | Not Started
Performance warnings report | Complete | Not Started
− Talent Management Reports | Complete | Not Started
└ Vacancy Succession Report | Complete | Not Started
└ Job Opening Report | Not Correct | Not Started | http://works.devss.net/hrms/vacancyreport.html
└ Candidates Report | Complete | Not Started
− Training Reports | Complete | Not Started
Training Reports | Complete | Not Started
− Time & Attendance Reports | Complete | Not Started
└ Projects Reports | Complete | Not Started
└ Employee Reports | Complete | Not Started
└ Attendance Summary | Complete | Not Started
└Monthly Attendance Summary | Complete | Not Started
− Leave Reports | Complete | Not Started
└ Leave Balances & Usage Report | Complete | Not Started
└ Leave Percentage Report | Complete | Not Started
− Organizational Reports | Complete | Not Started
Age chart | Complete | Not Started
Gender chart | Complete | Not Started
Department chart | Complete | Not Started
Job Title chart | Complete | Not Started
Location chart | Complete | Not Started
Manager chart | Complete | Not Started
Job status chart | Complete | Not Started
Organizational chart | Complete | Not Started
− Financial Reports | Complete | Not Started
Employee costs report | Complete | Not Started
Employee direct deposit details report | Complete | Not Started
Recruitment costs report | Complete | Not Started
- Benefits Reports | Design Pending | Not Started | Please all reports pages under the menu
- Scheduling Reports | Design Pending | Not Started | Please all reports pages under the menu
- Payroll Reports | Design Pending | Not Started | Please all reports pages under the menu
● Employees | Complete | Not Started
− Add Employee | Complete | Not Started
− Employee Profile | Complete | Not Started
- Missing Benefits sub page | Missing | Not Started | Please add a section for Employee Benefits on Employee Profile - allow admin the ability to manage employee benefits
- Missing Pay Details sub page(s) | Missing | Not Started | Ability to setup employee tax deductions (federal and state tax) benefit deductions, additional deductions, salary amount)
− Bulk Mass Update | Complete | Not Started
└ View Assets Equipment Assignment | Complete | Not Started
− Employee Reports | Complete | Not Started
└ Employee Report | Complete | Not Started
└ Head Count Report | Complete | Not Started
└ License Expiration Report | Complete | Not Started
└ Employee Turnover Hiring Report | Complete | Not Started
└ Employee Turnover Termination Report | Complete | Not Started
● Self Service | Complete | Not Started
− Personal Information | Complete | Not Started
- Personal Details | Complete | Not Started
- Contact Details | Complete | Not Started
- Emergency Contacts | Complete | Not Started
- Benefits | Design Pending | Not Started
- View Medical Insurance Details | Design Pending | Not Started
- Dependents | Complete | Not Started
- Citizenship Details | Complete | Not Started
- Reports To | Complete | Not Started
- Credentials | Complete | Not Started
- Memberships | Complete | Not Started
- Job History | Complete | Not Started
- Salary History | Complete | Not Started
- Direct Deposit | Complete | Not Started
− Time & Attendance | Complete | Not Started
- Timesheet | Complete | Not Started
− Punch In/Out | Complete | Not Started
− Attendance | Complete | Not Started
− Leave Information | Complete | Not Started
− Request Leave | Complete | Not Started
− Request Leave Status | Complete | Not Started
− Leave Balances | Complete | Not Started
− My Leave Balance and Usage Report | Complete | Not Started
− Time Off Calendar | Complete | Not Started
− Work Schedule | Design Pending | Not Started
− My Work Schedule - Design Pending | Design Pending | Not Started
− My Team Schedule - Design Pending | Design Pending | Not Started
− Work Schedule Request - Design Pending | Design Pending | Not Started
− Other Feature - Design Pending | Design Pending | Not Started
− Performance Reviews | Complete | Not Started
└ My Peer Reviewers | Complete | Not Started
└ My Warnings | Complete | Not Started
└ Peer Reviews | Complete | Not Started
└ My Goals | Complete | Not Started
└ My Appraisals | Complete | Not Started
− Training & Development | Complete | Not Started
└ Training Sessions | Complete | Not Started
└ My Training | Complete | Not Started
− Payroll Information | Pending Design | Not Started
└ My Paycheck Details | Pending Design | Not Started | Will also need the ability to view historical pay details
└ My Federal & Tax Details | Pending Design | Not Started | Effective Date update feature
└ View Pay Card | Design Pending | Not Started
− My Onboarding Tasks | Complete | Not Started
− My Company Equipment | Complete | Not Started
└ My Equipment | Complete | Not Started
− Give Props | Complete | Not Started | From here employees are able to Give out Props -- but we need a place on ALL Dashboards to see the employee Kudos - See Bamboohr for design on Employee profile
− My Props | Design Pending | Not Started
● Manager Self Service | Complete | Not Started
- My Organization | Complete | Not Started
- My Reports To | Complete | Not Started
- Employee List | Complete | Not Started
- My Onboarding Tasks | Complete | Not Started
−Time & Attendance | Complete | Not Started
- Employee Timesheet | Complete | Not Started | Review and Approve/Deny
- View Employee Attendance | Complete | Not Started
- Leave Management | Complete | Not Started
- Leave List | Complete | Not Started
− Employee Leave Balance | Complete | Not Started
− Assign Leave | Complete | Not Started | Review and Approve/Deny
− Leave Calendar | Complete | Not Started
- Performance Management | Complete | Not Started
− Peer Reviewers List | Complete | Not Started
− Employee Goals | Complete | Not Started
− Employee Appraisals | Complete | Not Started
- Talent Management | Complete | Not Started
− Candidates | Complete | Not Started
- Job Openings | Complete | Not Started
- Schedule Interview | Missing | Not Started | Need an ability to view recruitment calendar
- Schedule Management | Complete | Not Started
- Employee Schedules - Design Pending | Design Pending | Not Started
- Employee Schedules Request - Design Pending | Design Pending | Not Started
- Other Features - Design Pending | Design Pending | Not Started
− Manager Reports | Complete | Not Started
Employee job history report | Complete | Not Started
New hires report | Complete | Not Started
Employee Termination date | Complete | Not Started
Employee list report | Complete | Not Started
Employee contact list report | Complete | Not Started
Employee emergency contact report | Complete | Not Started
Employee timesheet report | Complete | Not Started
Employee length of service report | Complete | Not Started
Employee work contact report | Complete | Not Started
Employee start date | Complete | Not Started
Mandatory documents | Complete | Not Started
- Appraisal summary report | Complete | Not Started
- Review and Appraisal Progress Report | Complete | Not Started
- Performance Comparison Report | Complete | Not Started
- Employee Performance Profile | Complete | Not Started
- Performance Progress | Complete | Not Started
Performance warnings report | Complete | Not Started
Training Reports | Complete | Not Started
Attendance Summary | Complete | Not Started
└Monthly Attendance Summary | Complete | Not Started
Leave Balances & Usage Report | Complete | Not Started
Leave Percentage Report | Complete | Not Started
● Discipline | Complete | Not Started
- Discipline Cases | Complete | Not Started
− Configuration | Complete | Not Started
└ Disciplinary Document Templates | Menu Page Misspelled | Not Started | Please correct spelling
● Performance Management | Complete | Not Started
- Setup Peer Reviewers | Complete | Not Started
− Peer Reviewers List | Complete | Not Started
− Setup Competencies | Complete | Not Started
└ Competencies | Complete | Not Started
└ Competencies Mapping | Complete | Not Started
− Employee Goals | Complete | Not Started
└ Employee Goals | Complete | Not Started
− Employee Appraisals | Complete | Not Started
└ Employee Appraisals | Complete | Not Started
− Setup Appraisals | Complete | Not Started
└ Appraisals | Complete | Not Started
− Reports | Complete | Not Started
- Appraisal summary report | Complete | Not Started
Review and Appraisal Progress report | Complete | Not Started
Performance Comparison Report | Complete | Not Started
Employee Performance Profile | Complete | Not Started
Performance Progress | Complete | Not Started
- Performance warnings report | Complete | Not Started
● Talent Management | Complete | Not Started
− Candidates | Complete | Not Started
− Schedule Interview | Missing | Not Started | Need an ability to view recruitment calendar
− Job Openings | Complete | Not Started
− Setup Questions | Complete | Not Started
└ Interview Question Types | Complete | Not Started
└ Interview Questions | Complete | Not Started
− Setup Social Recruitment | Complete | Not Started
- Setup RSS Feed URL | Complete | Not Started
- Setup Webpage URL | Complete | Not Started
− Reports | Complete | Not Started
└ Vacancy Succession Report | Complete | Not Started
└ Job Opening Report | Not Correct | Not Started | http://works.devss.net/hrms/vacancyreport.html
└ Candidates Report | Complete | Not Started
● Time & Attendance | Complete | Not Started
− Timesheets | Complete | Not Started
└ Employee Timesheets | Complete | Not Started
└ Export Timesheets | Complete | Not Started
− Attendance | Complete | Not Started
└ Attendance | Complete | Not Started
└ Setup Time & Attendance | Complete | Not Started
└ Export Attendance | Complete | Not Started
└ Import Attendance | Complete | Not Started
− Reports | Complete | Not Started
└ Projects Reports | Complete | Not Started
└ Employee Reports | Complete | Not Started
└ Attendance Summary | Complete | Not Started
└Monthly Attendance Summary | Missing | Not Started
− Setup Project | Complete | Not Started
└ Customer | Complete | Not Started
└ Projects Information | Complete | Not Started
● Leave Management | Complete | Not Started
− Leave Balances | Complete | Not Started
└ Leave Information | Complete | Not Started
└ Employee Leave | Complete | Not Started
− Leave Approval Report | Complete | Not Started
− Leave Request | Complete | Not Started
− Leave Calendar | Complete | Not Started
− Reports | Complete | Not Started
└ Leave Balances & Usage Report | Complete | Not Started
└ Leave Percentage Report | Complete | Not Started
− Setup Leave | Complete | Not Started
└ Leave Period | Complete | Not Started
└ Leave Types | Complete | Not Started
└ Work Week | Complete | Not Started
└ Holidays | Complete | Not Started
└ Notifications | Complete | Not Started
● Benefits Administration | Complete | Not Started
− Setup Benefits - Design Pending | Design Pending | Not Started
− Maintain Employee Benefits - Design Pending | Design Pending | Not Started
− Benefit Reports | Design Pending | Not Started | Please all reports pages under the menu
● Schedule Management | Design Pending | Not Started
− Setup Schedule Management - Design Pending | Design Pending | Not Started
− Maintain Employee Schedules - Design Pending | Design Pending | Not Started
− Other Features - Design Pending | Design Pending | Not Started
− Schedule Reports - Design Pending | Design Pending | Not Started | Please all reports pages under the menu
● Payroll USA | Design Pending | Not Started
− Setup Payroll - Design Pending | Design Pending | Not Started
− Maintain Employee Payroll - Design Pending | Design Pending | Not Started
− Payroll Processing - Design Pending | Design Pending | Not Started
− Payroll Reports - Design Pending | Design Pending | Not Started | Please all reports pages under the menu
- Pay Card Setup | Design Pending | Not Started
● Training & Development | Complete | Not Started
− Training Administration | Complete | Not Started
└ Packages | Complete | Not Started
└ Courses | Complete | Not Started
└ Sessions | Complete | Not Started
− Reports | Complete | Not Started
Training Reports | Complete | Not Started
● Spring Extras | Complete | Not Started
− Calendar | Complete | Not Started
− Directory | Complete | Not Started
− Organization Chart | Complete | Not Started
− Documents | Complete | Not Started
− News | Complete | Not Started
− Events | Complete | Not Started
● Change Password - Top Right | Complete | Not Started
● Edit Profile - Top Right | Complete | Not Started
● Localization - Top Right | Complete | Not Started

## Details
Changes in Red | Changes in Red | Comments from Vicki
● Dashboard | http://works.devss.net/hrms/dashboard.html
● Spring Admin
− User Management
└ Users | http://works.devss.net/hrms/user.html | not correct add Modify Region featire: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/viewSystemUsers
└ User Roles | http://works.devss.net/hrms/userroles.html | not correct Edit Role page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/saveUserRole?id=13
− Configuration Setup SpringTools
└ Email Settings | http://works.devss.net/hrms/emailsettings.html | Fix edit feature & button http://works.devss.net/hrms/emailsettings.html
└ Email Subscription | http://works.devss.net/hrms/emailsubscriptions.html | Not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/viewEmailNotification
└ Localization | http://works.devss.net/hrms/localization.html | Not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/localization
└ Notifications | http://works.devss.net/hrms/notifications.html | Not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/notification/viewNotification
└ Open ID | http://works.devss.net/hrms/openid.html | Not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/openIdProvider
└ Authentication | http://works.devss.net/hrms/authentication.html | please fix the page -- left alignment
└ LDAP | http://works.devss.net/hrms/ldap.html | Fix edit feature & button http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/ldapAuthentication/configureLDAPAuthentication
− Audit Trail | http://works.devss.net/hrms/audittrail.html | Not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/audittrail/viewAuditTrail
− Auditing | http://works.devss.net/hrms/Audit.html
− Backups | http://works.devss.net/hrms/backup.html
− Delete Account
− Settings
└ Social Settings
└ Security Settings
− Manage My Account
● Company Core HR
− Setup Org Data
└ General Information | http://works.devss.net/hrms/organization-info.html | Fix edit feature & button http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/viewOrganizationGeneralInformation
└ Location | http://works.devss.net/hrms/org-location.html | Not correct - reclone http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/viewLocations
└ Department Structure | http://works.devss.net/hrms/orgchart.html | Not correct -- reclone http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/viewCompanyStructure#?
└ Configuration Setup Org Chart |  | please clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/orgChart/orgchartView
└ Define Setup Hierarchy | http://professional.demo.orangehrmlive.com/symfony/web/index.php/orgChart/defineJobTitleHierarchy | please clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/orgChart/defineJobTitleHierarchy
└ View Org Chart |  | please clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/orgChart/orgchartView
− Configuration Setup CoreHR
└ Optional Fields | http://works.devss.net/hrms/optionalfields.html | Validated
└ Custom Fields | http://works.devss.net/hrms/custom.html | Validated
└ Data Import | http://works.devss.net/hrms/data.html | fix the page -- align the fields
└ Reporting Methods | http://works.devss.net/hrms/rporting.html | Validated
└ Termination Reasons | http://works.devss.net/hrms/terminationreason.html | fix the page
− Setup Job Data
└ Job Titles | http://works.devss.net/hrms/jobtitle.html | Validated
└ Salary Components | http://works.devss.net/hrms/salarycomp.html | Validated
└ Pay Grades | http://works.devss.net/hrms/paygrades.html | missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/payGrade?payGradeId=2
└ Employment Status | http://works.devss.net/hrms/employmentstatus.html | Validated
└ Job Categories | http://works.devss.net/hrms/jobcategories.html | Validated
└ Work Shifts | http://works.devss.net/hrms/workshifts.html | Not correct -- reclone wth drop down values http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/workShift
− Setup Credentials
└ Skills | http://works.devss.net/hrms/skills.html | Validated
└ Licenses | http://works.devss.net/hrms/licenses.html | Validated
└ Education | http://works.devss.net/hrms/education.html | Validated
└ Languages | http://works.devss.net/hrms/languages.html | Validated
└ Memberships | http://works.devss.net/hrms/memberships.html | Validated
− Setup Nationalities | http://works.devss.net/hrms/nationalities.html | Validated
− Announcements Setup News & Documents
└ News | http://works.devss.net/hrms/news.html | Not correct -- http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/news/viewNewsList
└ News Categories | http://works.devss.net/hrms/news-categories.html | Please add a category field in news record and clone this page http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/news/viewCategoryList
└ Documents | http://works.devss.net/hrms/documents.html | reclone with edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/news/viewDocument/id/1
└ Document Categories | http://works.devss.net/hrms/document-categories.html | reclone with edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/news/viewCategoryList
− Set up Onboarding
└ Task Types | http://works.devss.net/hrms/tasking.html | fix add feature http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/onboarding/viewTaskTypes
└ Events | http://works.devss.net/hrms/events.html | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/onboarding/viewJobs/reset/1
− Assets Setup Equipment
└ Asset Brand Information | http://works.devss.net/hrms/brands.html | Add edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/asset/viewBrands/reset/1
└ Asset Categories | http://works.devss.net/hrms/categories.html | Add edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/asset/viewCategories/reset/1
└ View Assets Equipment Assignment | http://works.devss.net/hrms/assets.html | Add edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/asset/viewAssets/reset/1
└ Vendors | http://works.devss.net/hrms/vendors.html | Add edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/asset/viewVendorList
● HR Reports
− Onboarding Reports
└ Event Progress |  | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/onboarding/viewOnboardingReport/reportId/19
└ Participant Progress |  | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/onboarding/viewOnboardingReport/reportId/20
− Employee Reports
└ Employee Report | http://works.devss.net/hrms/employeereport.html | fix edit page as per orangehrm
└ Head Count Report | http://works.devss.net/hrms/headcount.html | fix page - fix edit report page as per orangehrm
└ License Expiration Report | http://works.devss.net/hrms/licenseexpiry.html | fix page - fix edit report page as per orangehrm
└ Employee Turnover Hiring Report | http://works.devss.net/hrms/turnoverhiring.html | fix page - fix edit report page as per orangehrm
└ Employee Turnover Termination Report | http://works.devss.net/hrms/turnovertermination.html | fix page - fix edit report page as per orangehrm
Employee diversity report | http://works.devss.net/hrms/Employeediversityreport.html
Employee custom fields | http://works.devss.net/hrms/Employeecustomfields.html
− Management Reports
Employee job history report | http://works.devss.net/hrms/jobhistoryreport.html
New hires report | http://works.devss.net/hrms/hiresreport.html
Employee Termination date | http://works.devss.net/hrms/empterminationreport.html
Employee list report | http://works.devss.net/hrms/employeelistreport.html
Employee contact list report | http://works.devss.net/hrms/Employeecontactlistreport.html
Employee emergency contact report | http://works.devss.net/hrms/Employeeemergencycontactreport.html
Employee timesheet report | http://works.devss.net/hrms/Employeetimesheetreport.html
Employee length of service report | http://works.devss.net/hrms/Employeelengthofservicereport.html
Employee work contact report | http://works.devss.net/hrms/Employeeworkcontactreport.html
Employee start date | http://works.devss.net/hrms/Employeestartdate.html
Mandatory documents | http://works.devss.net/hrms/Mandatorydocuments.html
− Performance Reports
Appraisal summary report | http://works.devss.net/hrms/appsummary.html
Performance warnings report | http://works.devss.net/hrms/warningreport.html
− Talent Management Reports
└ Vacancy Succession Report | http://works.devss.net/hrms/succession.html
└ Job Opening Report
└ Candidates Report | http://works.devss.net/hrms/research.html
− Training Reports
Training Reports |  | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/viewTrainingReport?reportId=4
− Time & Attendance Reports
└ Projects Reports |  | view page missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/displayProjectReport/reportId/1?backRequest=1
└ Employee Reports |  | view page missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/displayEmployeeReportCriteria/reportId/2
└ Attendance Summary |  | view page missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/displayAttendanceSummaryReportCriteria?reportId=4
− Reports
└ Leave Balances Entitlements & Usage Report |  | not correct -- reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeaveBalanceReport
└ Leave Percentage Report |  | missing please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeavePercentageReport/reportId/21
− Organizational Reports
Age chart | http://works.devss.net/hrms/Agechart.html
Gender chart | http://works.devss.net/hrms/gender.html
Department chart | http://works.devss.net/hrms/departmentchart.html
Job Title chart | http://works.devss.net/hrms/jobrolechart.html
Location chart | http://works.devss.net/hrms/locationchart.html
Manager chart | http://works.devss.net/hrms/managerchart.html
Job status chart | http://works.devss.net/hrms/jobstatuschart.html
Organizational chart | http://works.devss.net/hrms/view.html
− Financial Reports
Employee costs report
Employee direct deposit details report
Recruitment costs report
● Employees
− Add Employee | http://works.devss.net/hrms/add-employee.html | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/addEmployee
− Employee Profile - List | http://works.devss.net/hrms/employee-list.html | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewEmployeeList/reset/1
- Missing sub page | Personal Details | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewEmployee/empNumber/6
- Missing sub page | Contact Details | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/contactDetails/empNumber/6
- Missing sub page | Emergency Contacts | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewEmergencyContacts/empNumber/6
- Missing sub page | Dependents | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewDependents/empNumber/6
- Missing sub page | Immigration | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewImmigration/empNumber/6
- Missing sub page | Reports To | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewReportToDetails/empNumber/6
- Missing sub page | Qualifications | pleaes add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewQualifications/empNumber/6
- Missing sub page | Memberships | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewMemberships/empNumber/6
- Missing sub page | Job History | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewJobDetails/empNumber/6
- Missing sub page | Salary History | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewSalaryList/empNumber/6
- Missing sub page | Direct Deposit | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewDirectDepositDetails/empNumber/6
− Bulk Mass Update | http://works.devss.net/hrms/bulkupdate.html | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewBulkUpdater/reset/1
└ View Assets Equipment Assignment | http://works.devss.net/hrms/assets.html | Add edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/asset/viewAssets/reset/1
− Employee Reports
└ Employee Report | http://works.devss.net/hrms/employeereport.html | fix edit page as per orangehrm
└ Head Count Report | http://works.devss.net/hrms/headcount.html | fix page - fix edit report page as per orangehrm
└ License Expiration Report | http://works.devss.net/hrms/licenseexpiry.html | fix page - fix edit report page as per orangehrm
└ Employee Turnover Hiring Report | http://works.devss.net/hrms/turnoverhiring.html | fix page - fix edit report page as per orangehrm
└ Employee Turnover Termination Report | http://works.devss.net/hrms/turnovertermination.html | fix page - fix edit report page as per orangehrm
● Self Service
− Personal Information
- Personal Details | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewMyDetails
- Contact Details | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/contactDetails/empNumber/20
- Emergency Contacts | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewEmergencyContacts/empNumber/20
- Dependents | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewEmergencyContacts/empNumber/20
- Citizenship Details | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewImmigration/empNumber/20
- Reports To | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewReportToDetails/empNumber/20
- Credentials | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewQualifications/empNumber/20
- Memberships | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewMemberships/empNumber/20
- Job History | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewJobDetails/empNumber/20
- Salary History | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewSalaryList/empNumber/20
− Time Tracking
- Timesheet | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/time/viewMyTimesheet
− Clock In/Out
− Timeoff Requests | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/leave/viewMyLeaveList
− Work Schedule
- Request Schedule Change
− Performance Reviews
└ Appraisals
└ 360 Feedback Peer Reviews
└ Warnings
− Training
└ Training Courses
└ Training Requests
− Benefits
└ Benefit Information
− Payroll
└ Direct Deposit Information | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewDirectDepositDetails/empNumber/20
└ Paychecks
− Props | Kudos
● Manager Self Service
− Time & Attendance
- Timesheet Approval | Timesheets http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/time/viewEmployeeTimesheet
- Leave Request List | My Leave List http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/leave/viewLeaveList
- Time Off Request | Apply Leave http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/leave/applyLeave
- Schedule Change Request
● Performance Management
− Manage Trackers Setup Reviewers |  | not correct missing pages reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performanceTracker/addPerformanceTracker
− Employee Trackers Employee Reviewrs |  | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performanceTracker/addPerformanceTrackerLog/trackId/3
− Setup Competencies
└ Competencies y List |  | add edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performanceTracker/addPerformanceTrackerLog/trackId/3
└ Competencies y Mapping |  | not correct -- add missing Add page -- reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/competencyEmployeeGroups
− Employee Goals
└ Employee Goals |  | not correct - reclone All pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/viewEmployeeGoalList
− Employee Appraisals
└ Employee Appraisals |  | not correct - reclone All pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/viewAllAppraisals
− Configuration Setup Appraisals
└ Appraisals |  | not correct - reclone correctly: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/evaluatorGroupConfig
Missing sub page | Evaluators | add missing page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/evaluatorGroupConfig
Missing sub page | Questions | add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/viewQuestionList
Missing sub page | Form Format | add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/appraisalFormatGlobalConf
Missing sub page | Header Template | add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/viewAppraisalHeaderList
− Reports
- Appraisal summary report
- Performance warnings report
● Talent Management
− Candidates | http://works.devss.net/hrms/candidate.html | not correct please add edit feature on candidate name and reclone page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/addCandidate?id=13
− Vacancies Job Openings |  | not correct -- please reclone ALL features and workflow see Status sub pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/viewJobVacancy
Missing sub page | Edit Vacancy | Please clone ALL features: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/addJobVacancy?vacancyId=2
Missing sub page | Application Form | Please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/viewVacancyFormsListSimple/vacancyId/2
Missing sub page | Best Match Rule | Please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/viewVacancyFormsListSimple/vacancyId/2
− Configuration Setup Questions
└ Question Tags Interview Question Types |  | missing features reclone page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/viewVacancyQuestionTagList
└ Question Pools Interview Questions |  | not correct: please reclone all features: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/saveVacancyQuestion
− Reports
└ Vacancy Succession Report
└ Job Opening Report
└ Candidates Report
● Time & Attendance | http://works.devss.net/hrms/timesheet.html
− Timesheets
└ Timesheets | missing comment feature on edit timesheet | not correct please fix: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/editTimesheet?employeeId=5&timesheetId=127&actionName=viewTimesheet
└ Export to CSV Export Timesheets |  | not correct please reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/viewTimesheetCsvExtract
− Attendance
└ Attendance Records |  | not correct - please reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/attendance/viewAttendanceRecord
└ Configuration Setup Time & Attendance |  | page layout - missing buttons not correct - please reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/attendance/configure
└ Export Attendance to CVS |  | Validated
└ Import Attendance Data Upload |  | Validated
− Reports
└ Projects Reports |  | view page missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/displayProjectReport/reportId/1?backRequest=1
└ Employee Reports |  | view page missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/displayEmployeeReportCriteria/reportId/2
└ Attendance Summary |  | view page missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/displayAttendanceSummaryReportCriteria?reportId=4
− Setup Project
└ Customer |  | Validated perfer edit feature
└ Projects Information |  | not correct reclone http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/saveProject?projectId=3
● Leave Management | http://works.devss.net/hrms/timeoff.html
− Entitlements Leave Balances
└ Entitlement Leave Information |  | not correct - reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/addLeaveEntitlement
└ Employee Entitlements Leave |  | not correct -- reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeaveEntitlements/reset/1
− Leave Approval List Report |  | not correct - reclone all features: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeaveList/reset/1
− Assign Leave Request |  | not correct - reclone add check leave balances: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/assignLeave
− Leave Calendar | http://professional.demo.orangehrmlive.com/symfony/web/index.php/leave/showLeaveCalendar | not correct - clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/showLeaveCalendar
− Reports
└ Leave Balances Entitlements & Usage Report |  | not correct -- reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeaveBalanceReport
└ Leave Percentage Report |  | missing please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeavePercentageReport/reportId/21
− Configure Setup Leave
└ Leave Period |  | not correct -- reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeavePeriod
└ Leave Types |  | not correct -- reclonne: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeaveType and ADD missing pages from Leave Rule: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/leaveTypeList
Missing sub page | Leave Rule - General page | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeaveTypeRule?id=16
Missing sub page | Leave Rule - Who can apply page | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeaveTypeRuleWhoCanApply/id/16
Missing sub page | Leave Rule - Apply/Assign Restrictions page | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeaveTypeRuleApplyRestriction/id/16
Missing sub page | Leave Rule - Accural Rule page | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeaveTypeRuleAccrualRule/id/27
Missing sub page | Leave Rule - Carry Forward Rule page | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeaveTypeCarryForwardRule/id/27
└ Work Week |  | add all countries from drop down: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineWorkWeek
└ Holidays |  | add all countries from drop down: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewHolidayList
└ Notifications |  | fix fields on the page: the add column too wide: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeaveNotifications
● Benefits Administration
− Setup Benefits Programs | http://works.devss.net/hrms/bebefits.html -- fix spelling should be benefits
− Setup Benefit Types
− Benefits Enrollment
− Reports
● Schedule Management | please hurry and clone features before 15 day trial expires.
● Payroll USA | please hurry and clone features before 15 day trial expires.
● Training & Development
− Training Administration
└ Packages | http://works.devss.net/hrms/packages.html | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/viewPackageList
Missing sub page | Package Details | Add missing page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/addPackage
Missing sub page | Add Course | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/addCoursesToPackage/packageId/2
Missing sub page | Students | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/definePackageStudent/packageId/2
└ Courses | http://works.devss.net/hrms/course.html | not correct: reclone all pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/viewCourseList
Missing sub page | Course Details | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/addCourse
Missing sub page | Add Package | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/defineCoursePackage/courseId/3
└ Sessions | http://works.devss.net/hrms/sessiondetails.html | not correct -- reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/viewSessionList
Missing sub page | Session Details | Add missing page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/addSession
Missing sub page | Add Trainers | Add missing page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/defineSessionTrainer/sessionId/2
Missing sub page | Add Students | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/defineSessionStudent/sessionId/2
− Reports
Training Reports |  | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/viewTrainingReport?reportId=4
● Spring Extras
− Calendar | http://works.devss.net/hrms/cal.html
− Directory | http://works.devss.net/hrms/directory.html | please clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/directory/viewDirectory/reset/1
− Organization Chart | http://works.devss.net/hrms/view.html | please clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/orgChart/orgchartView
− Documents | http://works.devss.net/hrms/publishdoc.html | please clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/news/viewDocumentArticle/type/documents/status/published
− News | http://works.devss.net/hrms/publishnews.html | please add & clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/news/viewAnnouncementModule/type/news/status/published
*