## Summary
SpringHRM Menu & Pages | Design Status | Development Status | Design Complete | Development Complete
● Admin Dashboard | Design Not Complete | In Progress |  |  | Milestones
● Manager Dashboard | Design Not Complete | Not Started |  |  |  | Design Complete | 300
● Employee (Non Manager) Dashboard | Design Not Complete | Not Started |  |  |  | Development Complete | 525
● Spring Admin | Complete | Not Started |  |  |  | Website Complete | 525
− User Management | Complete | Not Started |  |  |  | SuperAdmin Complete | 525
└ Users | Complete | Not Started |  |  |  | Complete in my SaaS | 625
└ User Roles | Complete | Not Started
- Setup SpringTools | Complete | Not Started
└ Email Settings | Complete | Not Started
└ Email Subscription | Complete | Not Started
└ Localization | Complete | Not Started
└ Notifications | Complete | Not Started
└ Open ID | Complete | Not Started
└ Authentication | Complete | Not Started
└ LDAP | Complete | Not Started
- API Settings | Complete | Not Started
− Audit Trail | Complete | Not Started
− Auditing | Complete | Not Started
− Backups | Complete | Not Started
− Delete Account | Complete | Not Started
− Settings | Complete | Not Started
└ Social Settings | Complete | Not Started
└ Social Site Setup | Missing | Not Started
└ Security Settings | Complete | Not Started
− Manage My Account | Complete | Not Started
● Company Core HR | Complete | Not Started
− Setup Org Data | Complete | Not Started
└ General Information | Complete | Not Started
└ Location | Complete | Not Started
└ Department Structure | Complete | Not Started
└ Reporting Method | Complete | Not Started
└ Define Setup Hierarchy | Complete | Not Started
└ View Org Chart | Complete | Not Started
− Configuration Setup CoreHR | Complete | Not Started
└ Optional Fields | Complete | Not Started
└ Custom Fields | Complete | Not Started
└ Data Import | Complete | Not Started
└ Termination Reasons | Complete | Not Started
− Setup Job Data | Complete | Not Started
└ Job Titles | Complete | Not Started
└ Salary Components | Complete | Not Started
└ Pay Grades | Complete | Not Started
└ Employment Status | Complete | Not Started
└ Job Categories | Complete | Not Started
└ Work Shifts | Complete | Not Started
− Setup Credentials | Complete | Not Started
└ Skills | Complete | Not Started
└ Licenses | Complete | Not Started | http://works.devss.net/licenses.html ( add feature is added) | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/admin/viewLicenses
└ Education | Complete | Not Started
└ Languages | Complete | Not Started
└ Memberships | Complete | Not Started
− Setup Nationalities | Complete | Not Started
− Announcements Setup News & Documents | Complete | Not Started
└ News | Complete | Not Started
└ News Categories | Complete | Not Started
└ Documents | Complete | Not Started
└ Document Categories | Complete | Not Started
└ Events | complete | Not Started | http://works.devss.net/events.html
− Set up Onboarding | Complete | Not Started
└ Task Types | Complete | Not Started
└ Events | Complete | Not Started
− Assets Setup Equipment | Complete | Not Started
└ Asset Brand Information | Complete | Not Started
└ Asset Categories | Complete | Not Started
└ View Assets Equipment Assignment | Complete | Not Started
└ Vendors | Complete | Not Started
● HR Reports | Complete | Not Started
− Onboarding Reports | Complete | Not Started
└ Event Progress | Complete | Not Started
└ Participant Progress | Complete | Not Started
− Employee Reports | Complete | Not Started
└ Employee Report | Complete | Not Started
└ Head Count Report | Complete | Not Started
└ License Expiration Report | Complete | Not Started
└ Employee Turnover Hiring Report | Complete | Not Started
└ Employee Turnover Termination Report | Complete | Not Started
└ Employee Date of Birth | Complete | Not Started | http://works.devss.net/dob.html | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/pim/viewPimDefinedPredefinedReports/reportGroup/3/reportType/PIM_DEFINED
└ Employee Employees hired for each location | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/pim/viewPimDefinedPredefinedReports/reportGroup/3/reportType/PIM_DEFINED
└ Employee Employees hired for each sub-unit | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/pim/viewPimDefinedPredefinedReports/reportGroup/3/reportType/PIM_DEFINED
└ Employee Employees over 20 years | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/pim/viewPimDefinedPredefinedReports/reportGroup/3/reportType/PIM_DEFINED
└ Employee Employment Status of Employees | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/pim/viewPimDefinedPredefinedReports/reportGroup/3/reportType/PIM_DEFINED
└ Female Employee List with Service period over 1 year | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/pim/viewPimDefinedPredefinedReports/reportGroup/3/reportType/PIM_DEFINED
└ Employee Joined Date between 2010 - 2012 | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/pim/viewPimDefinedPredefinedReports/reportGroup/3/reportType/PIM_DEFINED
└ Employee Marital Status | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/pim/viewPimDefinedPredefinedReports/reportGroup/3/reportType/PIM_DEFINED
└ Employee PIM data verification | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/pim/viewPimDefinedPredefinedReports/reportGroup/3/reportType/PIM_DEFINED
└ Employee PIM Sample Report | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/pim/viewPimDefinedPredefinedReports/reportGroup/3/reportType/PIM_DEFINED
└ Employee Supervisor Subordinate Details | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/pim/viewPimDefinedPredefinedReports/reportGroup/3/reportType/PIM_DEFINED
Employee diversity report | Complete | Not Started
Employee custom fields | Complete | Not Started
− Management Reports | Complete | Not Started
Employee job history report | Complete | Not Started
New hires report | Complete | Not Started
Employee Termination date | Complete | Not Started
Employee list report | Complete | Not Started
Employee contact list report | Complete | Not Started
Employee emergency contact report | Complete | Not Started
Employee timesheet report | Complete | Not Started
Employee length of service report | Complete | Not Started
Employee work contact report | Complete | Not Started
Employee start date | Complete | Not Started
Mandatory documents | Complete | Not Started
− Performance Reports | Complete | Not Started
- Appraisal summary report | Not Correct | Not Started
Review and Appraisal Progress report | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/performance/viewPerformanceReport/reportId/43
Performance Comparison Report | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/performance/viewFullComparisonReport/reportId/44
Employee Performance Profile | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/performance/viewEmployeePerformanceProfile/reportId/45
Performance Progress | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/performance/viewPerformanceProgressReport/reportId/49
Performance warnings report | Complete | Not Started
− Talent Management Reports | Complete | Not Started
└ Vacancy Succession Report | Complete | Not Started
└ Job Opening Report | Not Correct | Not Started | This is not a report
└ Candidates Report | Complete | Not Started
− Training Reports | Complete | Not Started
Training Reports | Complete | Not Started
− Time & Attendance Reports | Complete | Not Started
└ Projects Reports | Complete | Not Started
└ Employee Reports | Complete | Not Started
└ Attendance Summary | Complete | Not Started
└Monthly Attendance Summary | Complete | Not Started | http://works.devss.net/monthattendance.html | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/time/displayAttendanceDetailsReport/reset/1
− Leave Reports | Complete | Not Started
└ Leave Balances Entitlements & Usage Report | Complete | Not Started
└ Leave Percentage Report | Complete | Not Started
− Organizational Reports | Complete | Not Started
Age chart | Complete | Not Started
Gender chart | Complete | Not Started
Department chart | Complete | Not Started
Job Title chart | Complete | Not Started
Location chart | Complete | Not Started
Manager chart | Complete | Not Started
Job status chart | Complete | Not Started
Organizational chart | Complete | Not Started
− Financial Reports | Complete | Not Started
Employee costs report | Complete | Not Started
Employee direct deposit details report | Complete | Not Started
Recruitment costs report | Complete | Not Started
- Benefits Reports | Complete | Not Started
- Scheduling Reports | Design Pending | Not Started
- Payroll Reports | Design Pending | Not Started
● Employees | Complete | Not Started
− Add Employee | Complete | Not Started
− Employee Profile - List | Complete | Not Started
- Missing sub page | Complete | Not Started
- Missing sub page | Complete | Not Started
- Missing sub page | Complete | Not Started
- Missing sub page | Complete | Not Started
- Missing sub page | Complete | Not Started
- Missing sub page | Complete | Not Started
- Missing sub page | Complete | Not Started
- Missing sub page | Complete | Not Started
- Missing sub page | Complete | Not Started
- Missing sub page | Complete | Not Started
- Missing sub page | Complete | Not Started
− Bulk Mass Update | Complete | Not Started
└ View Assets Equipment Assignment | Complete | Not Started
− Employee Reports | Complete | Not Started
└ Employee Report | Complete | Not Started
└ Head Count Report | Complete | Not Started
└ License Expiration Report | Complete | Not Started
└ Employee Turnover Hiring Report | Complete | Not Started
└ Employee Turnover Termination Report | Complete | Not Started
● Self Service | Complete | Not Started
− Personal Information | Complete | Not Started
- Personal Details | Complete | Not Started
- Contact Details | Complete | Not Started
- Emergency Contacts | Complete | Not Started
- Dependents | Complete | Not Started
- Citizenship Details | Complete | Not Started
- Reports To | Complete | Not Started
- Credentials | Complete | Not Started
- Memberships | Complete | Not Started
- Job History | Complete | Not Started
- Salary History | Complete | Not Started
- Direct Deposit | Complete | Not Started
− Time & Attendance | Complete | Not Started
- Timesheet | Complete | Not Started
− Punch In/Out | Complete | Not Started
− Attendance | Complete | Not Started
− Leave Information | Complete | Not Started
− Request Leave | Complete | Not Started
− Request Leave Status | Complete | Not Started
− Leave Balances | Complete | Not Started
− My Leave Balance and Usage Report | Complete | Not Started
− Time Off Calendar | Complete | Not Started
− Work Schedule | Design Pending | Not Started
- Team Schedule | Design Pending | Not Started
− Work Schedule | Design Pending | Not Started
- Request Schedule Change | Design Pending | Not Started
- Request Schedule Status | Design Pending | Not Started
− Performance Reviews | Complete | Not Started
└ My Peer Reviewers | Complete | Not Started
└ My Warnings | Complete | Not Started
└ Peer Reviews | Complete | Not Started
└ My Goals | Complete | Not Started
└ My Appraisals | Complete | Not Started
− Training & Development | Complete | Not Started
└ Training Sessions | Complete | Not Started
− Benefits Information | Complete | Not Started
└ Benefit Elections | Complete | Not Started
− Payroll Information | Complete | Not Started
└ View Paycheck | Design Pending | Not Started
└ Pay Card | Design Pending | Not Started
− My Onboarding Tasks | Complete | Not Started
− My Company Equipment | Complete | Not Started
└ My Equipment | Complete | Not Started
− Give Props | Complete | Not Started
● Manager Self Service | Complete | Not Started
- My Organization | Complete | Not Started
- My Reports To | Complete | Not Started
- Employee List | Complete | Not Started
- My Onboarding Tasks | Complete | Not Started
−Time & Attendance | Complete | Not Started
- Employee Timesheet | Complete | Not Started
- View Employee Attendance | Complete | Not Started
- Leave Management | Complete | Not Started
- Leave List | Complete | Not Started
− Employee Leave Balance | Complete | Not Started
− Assign Leave | Complete | Not Started
− Leave Calendar | Complete | Not Started
- Performance Management | Complete | Not Started
− Peer Reviewers List | Complete | Not Started
− Employee Goals | Complete | Not Started
− Employee Appraisals | Complete | Not Started
- Talent Management | Complete | Not Started
− Candidates | Complete | Not Started
- Job Openings | Complete | Not Started
- Schedule Management | Complete | Not Started
- Schedule Change Request? | Design Pending | Not Started
- Team Work Schedule? | Design Pending | Not Started
− Manager Reports | Complete | Not Started
Employee job history report | Complete | Not Started
New hires report | Complete | Not Started
Employee Termination date | Complete | Not Started
Employee list report | Complete | Not Started
Employee contact list report | Complete | Not Started
Employee emergency contact report | Complete | Not Started
Employee timesheet report | Complete | Not Started
Employee length of service report | Complete | Not Started
Employee work contact report | Complete | Not Started
Employee start date | Complete | Not Started
Mandatory documents | Complete | Not Started
- Appraisal summary report | Not Correct | Not Started
Review and Appraisal Progress report | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/performance/viewPerformanceReport/reportId/43
Performance Comparison Report | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/performance/viewFullComparisonReport/reportId/44
Employee Performance Profile | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/performance/viewEmployeePerformanceProfile/reportId/45
Performance Progress | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/performance/viewPerformanceProgressReport/reportId/49
Performance warnings report | Complete | Not Started
Training Reports | Complete | Not Started
Attendance Summary | Complete | Not Started
└Monthly Attendance Summary | Complete | Not Started | http://works.devss.net/monthattendance.html | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/time/displayAttendanceDetailsReport/reset/1
Leave Balances & Usage Report | Complete | Not Started
Leave Percentage Report | Complete | Not Started
● Discipline | Complete | Not Started
- Discipline Cases | Complete | Not Started | http://works.devss.net/disciplinecases.html | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/discipline/viewDisciplinaryCases
− Configuration | Missing | Not Started
└ Discoplinary Document Templates | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/discipline/viewDisciplinaryDocumentTemplates
● Performance Management | Complete | Not Started
- Setup Peer Reviewers | Complete | Not Started
− Peer Reviewers List | Complete | Not Started
− Setup Competencies | Complete | Not Started
└ Competencies y List | Complete | Not Started
└ Competencies y Mapping | Complete | Not Started
− Employee Goals | Complete | Not Started
└ Employee Goals | Complete | Not Started
− Employee Appraisals | Complete | Not Started
└ Employee Appraisals | Complete | Not Started
Missing sub page | Complete | Not Started
Missing sub page | Complete | Not Started
Missing sub page | Complete | Not Started
− Configuration Setup Appraisals | Complete | Not Started
└ Appraisals | Complete | Not Started
Missing sub page | Complete | Not Started
Missing sub page | Complete | Not Started
Missing sub page | Complete | Not Started
Missing sub page | Complete | Not Started
− Reports | Complete | Not Started
- Appraisal summary report | Complete | Not Started
- Performance warnings report | Complete | Not Started
- Review and Appraisal Progress Report | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/performance/viewPerformanceReport/reportId/43
- Performance Comparison Report | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/performance/viewFullComparisonReport/reportId/44
- Employee Performance Profile | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/performance/viewEmployeePerformanceProfile/reportId/45
- Performance Progress | Missing | Not Started | http://vickia.trial49.orangehrmlive.com/symfony/web/index.php/performance/viewPerformanceProgressReport/reportId/49
● Talent Management | Complete | Not Started
− Candidates | Complete | Not Started
− Vacancies Job Openings | Complete | Not Started
Missing sub page | Complete | Not Started
Missing sub page | Complete | Not Started
Missing sub page | Complete | Not Started
− Configuration Setup Questions | Complete | Not Started
└ Question Tags Interview Question Types | Complete | Not Started
└ Question Pools Interview Questions | Complete | Not Started
− Setup Social Recruitment | Complete | Not Started
- Setup RSS Feed URL | Complete | Not Started
- Setup Webpage URL | Complete | Not Started
− Reports | Complete | Not Started
└ Vacancy Succession Report | Complete | Not Started
└ Job Opening Report | Wrong Page | Not Started | This is not a report
└ Candidates Report | Complete | Not Started
● Time & Attendance | Complete | Not Started
− Timesheets | Complete | Not Started
└ Employee Timesheets | Complete | Not Started
└ Export to CSV Export Timesheets | Complete | Not Started
− Attendance | Complete | Not Started
└ Attendance Records | Complete | Not Started
└ Configuration Setup Time & Attendance | Complete | Not Started
└ Export Attendance to CVS | Complete | Not Started
└ Import Attendance Data Upload | Complete | Not Started
− Reports | Complete | Not Started
└ Projects Reports | Complete | Not Started
└ Employee Reports | Complete | Not Started
└ Attendance Summary | Complete | Not Started
− Setup Project | Complete | Not Started
└ Customer | Complete | Not Started
└ Projects Information | Complete | Not Started
● Leave Management | Complete | Not Started
− Entitlements Leave Balances | Complete | Not Started
└ Entitlement Leave Information | Complete | Not Started
└ Employee Entitlements Leave | Complete | Not Started
− Leave Approval List Report | Complete | Not Started
− Assign Leave Request | Complete | Not Started
− Leave Calendar | Complete | Not Started
− Reports | Complete | Not Started
└ Leave Balances Entitlements & Usage Report | Complete | Not Started
└ Leave Percentage Report | Complete | Not Started
− Configure Setup Leave | Complete | Not Started
└ Leave Period | Complete | Not Started
└ Leave Types | Complete | Not Started
└ Work Week | Complete | Not Started
└ Holidays | Complete | Not Started
└ Notifications | Complete | Not Started
● Benefits Administration | Complete | Not Started
− Setup Benefits Programs | Design Pending | Not Started
− Setup Benefit Types | Design Pending | Not Started
− Benefits Enrollment | Complete | Not Started | benefits history
− Reports | Complete | Not Started
● Schedule Management | Design Pending | Not Started
Features | Design Pending | Not Started
Features | Design Pending | Not Started
Features | Design Pending | Not Started
Features | Design Pending | Not Started
● Payroll USA | Design Pending | Not Started
- Pay Card Setup | Design Pending | Not Started
● Training & Development | Complete | Not Started
− Training Administration | Complete | Not Started
└ Packages | Complete | Not Started
└ Courses | Complete | Not Started
└ Sessions | Complete | Not Started
− Reports | Complete | Not Started
Training Reports | Complete | Not Started
● Spring Extras | Complete | Not Started
− Calendar | Complete | Not Started
− Directory | Complete | Not Started
− Organization Chart | Complete | Not Started
− Documents | Complete | Not Started
− News | Complete | Not Started
− Events | Complete | Not Started
● Edit Profile - Top Right | Complete | Not Started | works.devss.net/edit-myprofile.html