## Summary
SpringHRM Menu & Pages | Design Status | Date to Complete | Notes | Development Complete
● Admin Dashboard | Design Not Complete | Not Started
● Manager Dashboard | Design Not Complete | Not Started
● Employee (Non Manager) Dashboard | Design Not Complete | Not Started
● Spring Admin | Complete | Not Started
− User Management | Complete | Not Started
└ Users | Complete | Not Started
└ User Roles | Complete | Not Started
- Setup SpringTools | Complete | Not Started
└ Dashboard Settings | Missing | Not Started | See dashboard design
└ Email Settings | Complete | Not Started
└ Email Subscription | Complete | Not Started
└ Localization | Complete | Not Started
└ Notifications | Complete | Not Started
└ Open ID | Complete | Not Started
└ Authentication | Complete | Not Started
└ LDAP | Complete | Not Started
- API Settings | Complete | Not Started
− Audit Trail | Complete | Not Started
− Auditing | Complete | Not Started
− Backups | Complete | Not Started
− Delete Account | Complete | Not Started
− Settings | Complete | Not Started
└ Social Settings | Complete | Not Started
└ Social Site Settings | Not Correct | Not Started | See Hip Chat for functionality
└ Security Settings | Complete | Not Started
− Manage My Account | Need to Update | Not Started | Please update Edit Subscription page
● Core HR | Complete | Not Started
− Setup Org Data | Complete | Not Started
└ General Information | Complete | Not Started
└ Location | Complete | Not Started
└ Department Structure | Complete | Not Started
└ Reporting Method | Complete | Not Started
└ Define Setup Hierarchy | Complete | Not Started
└ View Org Chart | Complete | Not Started
− Setup CoreHR | Complete | Not Started
└ Optional Fields | Complete | Not Started
└ Custom Fields | Complete | Not Started
└ Data Import | Complete | Not Started
└ Termination Reasons | Complete | Not Started
− Setup Job Data | Complete | Not Started
└ Job Titles | Complete | Not Started
└ Salary Components | Complete | Not Started
└ Pay Grades | Complete | Not Started
└ Employment Status | Complete | Not Started
└ Job Categories | Complete | Not Started
└ Work Shifts | Complete | Not Started
− Setup Credentials | Complete | Not Started
└ Skills | Complete | Not Started
└ Licenses | Complete | Not Started
└ Education | Complete | Not Started
└ Languages | Complete | Not Started
└ Memberships | Complete | Not Started
− Setup Nationalities | Complete | Not Started
− Setup News & Documents | Complete | Not Started
└ News | Complete | Not Started
└ News Categories | Complete | Not Started
└ Documents | Complete | Not Started
└ Document Categories | Complete | Not Started
└ Events | Complete | Not Started
− Set up Onboarding | Complete | Not Started
└ Task Types | Complete | Not Started
└ Events | Complete | Not Started
− Assets Setup Equipment | Complete | Not Started
└ Asset Brand Information | Complete | Not Started
└ Asset Categories | Complete | Not Started
└ View Assets Equipment Assignment | Complete | Not Started
└ Vendors | Complete | Not Started
● HR Reports | Complete | Not Started
− Onboarding Reports | Complete | Not Started
└ Event Progress | Complete | Not Started
└ Participant Progress | Complete | Not Started
− Employee Reports | Complete | Not Started
└ Employee Report | Complete | Not Started
└ Head Count Report | Complete | Not Started
└ License Expiration Report | Complete | Not Started
└ Employee Turnover Hiring Report | Complete | Not Started
└ Employee Turnover Termination Report | Complete | Not Started
Employee diversity report | Complete | Not Started
Employee custom fields | Complete | Not Started
└ Employee Date of Birth | Complete | Not Started
└ Employee Employees hired for each location | Complete | Not Started
└ Employee Employees hired for each sub-unit | Complete | Not Started
└ Employee Employees over 20 years | Complete | Not Started
└ Employee Employment Status of Employees | Complete | Not Started
└ Female Employee List with Service period over 1 year | Complete | Not Started
└ Employee Joined Date between 2010 - 2012 | Complete | Not Started
└ Employee Marital Status | Complete | Not Started
└ Employee PIM data verification | Complete | Not Started
└ Employee PIM Sample Report | Complete | Not Started
└ Employee Supervisor Subordinate Details | Complete | Not Started
− Management Reports | Complete | Not Started
Employee job history report | Complete | Not Started
New hires report | Complete | Not Started
Employee Termination date | Complete | Not Started
Employee list report | Complete | Not Started
Employee contact list report | Complete | Not Started
Employee emergency contact report | Complete | Not Started
Employee timesheet report | Complete | Not Started
Employee length of service report | Complete | Not Started
Employee work contact report | Complete | Not Started
Employee start date | Complete | Not Started
Mandatory documents | Complete | Not Started
− Performance Reports | Complete | Not Started
- Appraisal summary report | Complete | Not Started
Review and Appraisal Progress report | Complete | Not Started
Performance Comparison Report | Complete | Not Started
Employee Performance Profile | Complete | Not Started
Performance Progress | Complete | Not Started
Performance warnings report | Complete | Not Started
− Talent Management Reports | Complete | Not Started
└ Vacancy Succession Report | Complete | Not Started
└ Job Opening Report | Not Correct | Not Started | http://works.devss.net/hrms/vacancyreport.html
└ Candidates Report | Complete | Not Started
− Training Reports | Complete | Not Started
Training Reports | Complete | Not Started
− Time & Attendance Reports | Complete | Not Started
└ Projects Reports | Complete | Not Started
└ Employee Reports | Complete | Not Started
└ Attendance Summary | Complete | Not Started
└Monthly Attendance Summary | Complete | Not Started
− Leave Reports | Complete | Not Started
└ Leave Balances & Usage Report | Complete | Not Started
└ Leave Percentage Report | Complete | Not Started
− Organizational Reports | Complete | Not Started
Age chart | Complete | Not Started
Gender chart | Complete | Not Started
Department chart | Complete | Not Started
Job Title chart | Complete | Not Started
Location chart | Complete | Not Started
Manager chart | Complete | Not Started
Job status chart | Complete | Not Started
Organizational chart | Complete | Not Started
− Financial Reports | Complete | Not Started
Employee costs report | Complete | Not Started
Employee direct deposit details report | Complete | Not Started
Recruitment costs report | Complete | Not Started
- Benefits Reports | Design Pending | Not Started | Please all reports pages under the menu
- Scheduling Reports | Design Pending | Not Started | Please all reports pages under the menu
- Payroll Reports | Design Pending | Not Started | Please all reports pages under the menu
● Employees | Complete | Not Started
− Add Employee | Complete | Not Started
− Employee Profile | Complete | Not Started
- Missing Benefits sub page | Missing | Not Started | Please add a section for Employee Benefits on Employee Profile - allow admin the ability to manage employee benefits
- Missing Pay Details sub page(s) | Missing | Not Started | Ability to setup employee tax deductions (federal and state tax) benefit deductions, additional deductions, salary amount)
− Bulk Mass Update | Complete | Not Started
└ View Assets Equipment Assignment | Complete | Not Started
− Employee Reports | Complete | Not Started
└ Employee Report | Complete | Not Started
└ Head Count Report | Complete | Not Started
└ License Expiration Report | Complete | Not Started
└ Employee Turnover Hiring Report | Complete | Not Started
└ Employee Turnover Termination Report | Complete | Not Started
● Self Service | Complete | Not Started
− Personal Information | Complete | Not Started
- Personal Details | Complete | Not Started
- Contact Details | Complete | Not Started
- Emergency Contacts | Complete | Not Started
- Benefits | Design Pending | Not Started
- View Medical Insurance Details | Design Pending | Not Started
- Dependents | Complete | Not Started
- Citizenship Details | Complete | Not Started
- Reports To | Complete | Not Started
- Credentials | Complete | Not Started
- Memberships | Complete | Not Started
- Job History | Complete | Not Started
- Salary History | Complete | Not Started
- Direct Deposit | Complete | Not Started
− Time & Attendance | Complete | Not Started
- Timesheet | Complete | Not Started
− Punch In/Out | Complete | Not Started
− Attendance | Complete | Not Started
− Leave Information | Complete | Not Started
− Request Leave | Complete | Not Started
− Request Leave Status | Complete | Not Started
− Leave Balances | Complete | Not Started
− My Leave Balance and Usage Report | Complete | Not Started
− Time Off Calendar | Complete | Not Started
− Work Schedule | Design Pending | Not Started
− My Work Schedule - Design Pending | Design Pending | Not Started
− My Team Schedule - Design Pending | Design Pending | Not Started
− Work Schedule Request - Design Pending | Design Pending | Not Started
− Other Feature - Design Pending | Design Pending | Not Started
− Performance Reviews | Complete | Not Started
└ My Peer Reviewers | Complete | Not Started
└ My Warnings | Complete | Not Started
└ Peer Reviews | Complete | Not Started
└ My Goals | Complete | Not Started
└ My Appraisals | Complete | Not Started
− Training & Development | Complete | Not Started
└ Training Sessions | Complete | Not Started
└ My Training | Complete | Not Started
− Payroll Information | Pending Design | Not Started
└ My Paycheck Details | Pending Design | Not Started | Will also need the ability to view historical pay details
└ My Federal & Tax Details | Pending Design | Not Started | Effective Date update feature
└ View Pay Card | Design Pending | Not Started
− My Onboarding Tasks | Complete | Not Started
− My Company Equipment | Complete | Not Started
└ My Equipment | Complete | Not Started
− Give Props | Complete | Not Started | From here employees are able to Give out Props -- but we need a place on ALL Dashboards to see the employee Kudos - See Bamboohr for design on Employee profile
− My Props | Design Pending | Not Started
● Manager Self Service | Complete | Not Started
- My Organization | Complete | Not Started
- My Reports To | Complete | Not Started
- Employee List | Complete | Not Started
- My Onboarding Tasks | Complete | Not Started
−Time & Attendance | Complete | Not Started
- Employee Timesheet | Complete | Not Started | Review and Approve/Deny
- View Employee Attendance | Complete | Not Started
- Leave Management | Complete | Not Started
- Leave List | Complete | Not Started
− Employee Leave Balance | Complete | Not Started
− Assign Leave | Complete | Not Started | Review and Approve/Deny
− Leave Calendar | Complete | Not Started
- Performance Management | Complete | Not Started
− Peer Reviewers List | Complete | Not Started
− Employee Goals | Complete | Not Started
− Employee Appraisals | Complete | Not Started
- Talent Management | Complete | Not Started
− Candidates | Complete | Not Started
- Job Openings | Complete | Not Started
- Schedule Interview | Missing | Not Started | Need an ability to view recruitment calendar
- Schedule Management | Complete | Not Started
- Employee Schedules - Design Pending | Design Pending | Not Started
- Employee Schedules Request - Design Pending | Design Pending | Not Started
- Other Features - Design Pending | Design Pending | Not Started
− Manager Reports | Complete | Not Started
Employee job history report | Complete | Not Started
New hires report | Complete | Not Started
Employee Termination date | Complete | Not Started
Employee list report | Complete | Not Started
Employee contact list report | Complete | Not Started
Employee emergency contact report | Complete | Not Started
Employee timesheet report | Complete | Not Started
Employee length of service report | Complete | Not Started
Employee work contact report | Complete | Not Started
Employee start date | Complete | Not Started
Mandatory documents | Complete | Not Started
- Appraisal summary report | Complete | Not Started
- Review and Appraisal Progress Report | Complete | Not Started
- Performance Comparison Report | Complete | Not Started
- Employee Performance Profile | Complete | Not Started
- Performance Progress | Complete | Not Started
Performance warnings report | Complete | Not Started
Training Reports | Complete | Not Started
Attendance Summary | Complete | Not Started
└Monthly Attendance Summary | Complete | Not Started
Leave Balances & Usage Report | Complete | Not Started
Leave Percentage Report | Complete | Not Started
● Discipline | Complete | Not Started
- Discipline Cases | Complete | Not Started
− Configuration | Complete | Not Started
└ Disciplinary Document Templates | Menu Page Misspelled | Not Started | Please correct spelling
● Performance Management | Complete | Not Started
- Setup Peer Reviewers | Complete | Not Started
− Peer Reviewers List | Complete | Not Started
− Setup Competencies | Complete | Not Started
└ Competencies | Complete | Not Started
└ Competencies Mapping | Complete | Not Started
− Employee Goals | Complete | Not Started
└ Employee Goals | Complete | Not Started
− Employee Appraisals | Complete | Not Started
└ Employee Appraisals | Complete | Not Started
− Setup Appraisals | Complete | Not Started
└ Appraisals | Complete | Not Started
− Reports | Complete | Not Started
- Appraisal summary report | Complete | Not Started
Review and Appraisal Progress report | Complete | Not Started
Performance Comparison Report | Complete | Not Started
Employee Performance Profile | Complete | Not Started
Performance Progress | Complete | Not Started
- Performance warnings report | Complete | Not Started
● Talent Management | Complete | Not Started
− Candidates | Complete | Not Started
− Schedule Interview | Missing | Not Started | Need an ability to view recruitment calendar
− Job Openings | Complete | Not Started
− Setup Questions | Complete | Not Started
└ Interview Question Types | Complete | Not Started
└ Interview Questions | Complete | Not Started
− Setup Social Recruitment | Complete | Not Started
- Setup RSS Feed URL | Complete | Not Started
- Setup Webpage URL | Complete | Not Started
− Reports | Complete | Not Started
└ Vacancy Succession Report | Complete | Not Started
└ Job Opening Report | Not Correct | Not Started | http://works.devss.net/hrms/vacancyreport.html
└ Candidates Report | Complete | Not Started
● Time & Attendance | Complete | Not Started
− Timesheets | Complete | Not Started
└ Employee Timesheets | Complete | Not Started
└ Export Timesheets | Complete | Not Started
− Attendance | Complete | Not Started
└ Attendance | Complete | Not Started
└ Setup Time & Attendance | Complete | Not Started
└ Export Attendance | Complete | Not Started
└ Import Attendance | Complete | Not Started
− Reports | Complete | Not Started
└ Projects Reports | Complete | Not Started
└ Employee Reports | Complete | Not Started
└ Attendance Summary | Complete | Not Started
└Monthly Attendance Summary | Missing | Not Started
− Setup Project | Complete | Not Started
└ Customer | Complete | Not Started
└ Projects Information | Complete | Not Started
● Leave Management | Complete | Not Started
− Leave Balances | Complete | Not Started
└ Leave Information | Complete | Not Started
└ Employee Leave | Complete | Not Started
− Leave Approval Report | Complete | Not Started
− Leave Request | Complete | Not Started
− Leave Calendar | Complete | Not Started
− Reports | Complete | Not Started
└ Leave Balances & Usage Report | Complete | Not Started
└ Leave Percentage Report | Complete | Not Started
− Setup Leave | Complete | Not Started
└ Leave Period | Complete | Not Started
└ Leave Types | Complete | Not Started
└ Work Week | Complete | Not Started
└ Holidays | Complete | Not Started
└ Notifications | Complete | Not Started
● Benefits Administration | Complete | Not Started
− Setup Benefits - Design Pending | Design Pending | Not Started
− Maintain Employee Benefits - Design Pending | Design Pending | Not Started
− Benefit Reports | Design Pending | Not Started | Please all reports pages under the menu
● Schedule Management | Design Pending | Not Started
− Setup Schedule Management - Design Pending | Design Pending | Not Started
− Maintain Employee Schedules - Design Pending | Design Pending | Not Started
− Other Features - Design Pending | Design Pending | Not Started
− Schedule Reports - Design Pending | Design Pending | Not Started | Please all reports pages under the menu
● Payroll USA | Design Pending | Not Started
− Setup Payroll - Design Pending | Design Pending | Not Started
− Maintain Employee Payroll - Design Pending | Design Pending | Not Started
− Payroll Processing - Design Pending | Design Pending | Not Started
− Payroll Reports - Design Pending | Design Pending | Not Started | Please all reports pages under the menu
- Pay Card Setup | Design Pending | Not Started
● Training & Development | Complete | Not Started
− Training Administration | Complete | Not Started
└ Packages | Complete | Not Started
└ Courses | Complete | Not Started
└ Sessions | Complete | Not Started
− Reports | Complete | Not Started
Training Reports | Complete | Not Started
● Spring Extras | Complete | Not Started
− Calendar | Complete | Not Started
− Directory | Complete | Not Started
− Organization Chart | Complete | Not Started
− Documents | Complete | Not Started
− News | Complete | Not Started
− Events | Complete | Not Started
● Change Password - Top Right | Complete | Not Started
● Edit Profile - Top Right | Complete | Not Started
● Localization - Top Right | Complete | Not Started

## Details
Changes in Red | Changes in Red | Comments from Vicki
● Dashboard | http://works.devss.net/hrms/dashboard.html
● Spring Admin
− User Management
└ Users | http://works.devss.net/hrms/user.html | not correct add Modify Region featire: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/viewSystemUsers
└ User Roles | http://works.devss.net/hrms/userroles.html | not correct Edit Role page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/saveUserRole?id=13
− Configuration Setup SpringTools
└ Email Settings | http://works.devss.net/hrms/emailsettings.html | Fix edit feature & button http://works.devss.net/hrms/emailsettings.html
└ Email Subscription | http://works.devss.net/hrms/emailsubscriptions.html | Not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/viewEmailNotification
└ Localization | http://works.devss.net/hrms/localization.html | Not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/localization
└ Notifications | http://works.devss.net/hrms/notifications.html | Not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/notification/viewNotification
└ Open ID | http://works.devss.net/hrms/openid.html | Not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/openIdProvider
└ Authentication | http://works.devss.net/hrms/authentication.html | please fix the page -- left alignment
└ LDAP | http://works.devss.net/hrms/ldap.html | Fix edit feature & button http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/ldapAuthentication/configureLDAPAuthentication
− Audit Trail | http://works.devss.net/hrms/audittrail.html | Not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/audittrail/viewAuditTrail
− Auditing | http://works.devss.net/hrms/Audit.html
− Backups | http://works.devss.net/hrms/backup.html
− Delete Account
− Settings
└ Social Settings
└ Security Settings
− Manage My Account
● Company Core HR
− Setup Org Data
└ General Information | http://works.devss.net/hrms/organization-info.html | Fix edit feature & button http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/viewOrganizationGeneralInformation
└ Location | http://works.devss.net/hrms/org-location.html | Not correct - reclone http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/viewLocations
└ Department Structure | http://works.devss.net/hrms/orgchart.html | Not correct -- reclone http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/viewCompanyStructure#?
└ Configuration Setup Org Chart |  | please clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/orgChart/orgchartView
└ Define Setup Hierarchy | http://professional.demo.orangehrmlive.com/symfony/web/index.php/orgChart/defineJobTitleHierarchy | please clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/orgChart/defineJobTitleHierarchy
└ View Org Chart |  | please clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/orgChart/orgchartView
− Configuration Setup CoreHR
└ Optional Fields | http://works.devss.net/hrms/optionalfields.html | Validated
└ Custom Fields | http://works.devss.net/hrms/custom.html | Validated
└ Data Import | http://works.devss.net/hrms/data.html | fix the page -- align the fields
└ Reporting Methods | http://works.devss.net/hrms/rporting.html | Validated
└ Termination Reasons | http://works.devss.net/hrms/terminationreason.html | fix the page
− Setup Job Data
└ Job Titles | http://works.devss.net/hrms/jobtitle.html | Validated
└ Salary Components | http://works.devss.net/hrms/salarycomp.html | Validated
└ Pay Grades | http://works.devss.net/hrms/paygrades.html | missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/payGrade?payGradeId=2
└ Employment Status | http://works.devss.net/hrms/employmentstatus.html | Validated
└ Job Categories | http://works.devss.net/hrms/jobcategories.html | Validated
└ Work Shifts | http://works.devss.net/hrms/workshifts.html | Not correct -- reclone wth drop down values http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/workShift
− Setup Credentials
└ Skills | http://works.devss.net/hrms/skills.html | Validated
└ Licenses | http://works.devss.net/hrms/licenses.html | Validated
└ Education | http://works.devss.net/hrms/education.html | Validated
└ Languages | http://works.devss.net/hrms/languages.html | Validated
└ Memberships | http://works.devss.net/hrms/memberships.html | Validated
− Setup Nationalities | http://works.devss.net/hrms/nationalities.html | Validated
− Announcements Setup News & Documents
└ News | http://works.devss.net/hrms/news.html | Not correct -- http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/news/viewNewsList
└ News Categories | http://works.devss.net/hrms/news-categories.html | Please add a category field in news record and clone this page http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/news/viewCategoryList
└ Documents | http://works.devss.net/hrms/documents.html | reclone with edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/news/viewDocument/id/1
└ Document Categories | http://works.devss.net/hrms/document-categories.html | reclone with edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/news/viewCategoryList
− Set up Onboarding
└ Task Types | http://works.devss.net/hrms/tasking.html | fix add feature http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/onboarding/viewTaskTypes
└ Events | http://works.devss.net/hrms/events.html | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/onboarding/viewJobs/reset/1
− Assets Setup Equipment
└ Asset Brand Information | http://works.devss.net/hrms/brands.html | Add edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/asset/viewBrands/reset/1
└ Asset Categories | http://works.devss.net/hrms/categories.html | Add edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/asset/viewCategories/reset/1
└ View Assets Equipment Assignment | http://works.devss.net/hrms/assets.html | Add edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/asset/viewAssets/reset/1
└ Vendors | http://works.devss.net/hrms/vendors.html | Add edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/asset/viewVendorList
● HR Reports
− Onboarding Reports
└ Event Progress |  | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/onboarding/viewOnboardingReport/reportId/19
└ Participant Progress |  | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/onboarding/viewOnboardingReport/reportId/20
− Employee Reports
└ Employee Report | http://works.devss.net/hrms/employeereport.html | fix edit page as per orangehrm
└ Head Count Report | http://works.devss.net/hrms/headcount.html | fix page - fix edit report page as per orangehrm
└ License Expiration Report | http://works.devss.net/hrms/licenseexpiry.html | fix page - fix edit report page as per orangehrm
└ Employee Turnover Hiring Report | http://works.devss.net/hrms/turnoverhiring.html | fix page - fix edit report page as per orangehrm
└ Employee Turnover Termination Report | http://works.devss.net/hrms/turnovertermination.html | fix page - fix edit report page as per orangehrm
Employee diversity report | http://works.devss.net/hrms/Employeediversityreport.html
Employee custom fields | http://works.devss.net/hrms/Employeecustomfields.html
− Management Reports
Employee job history report | http://works.devss.net/hrms/jobhistoryreport.html
New hires report | http://works.devss.net/hrms/hiresreport.html
Employee Termination date | http://works.devss.net/hrms/empterminationreport.html
Employee list report | http://works.devss.net/hrms/employeelistreport.html
Employee contact list report | http://works.devss.net/hrms/Employeecontactlistreport.html
Employee emergency contact report | http://works.devss.net/hrms/Employeeemergencycontactreport.html
Employee timesheet report | http://works.devss.net/hrms/Employeetimesheetreport.html
Employee length of service report | http://works.devss.net/hrms/Employeelengthofservicereport.html
Employee work contact report | http://works.devss.net/hrms/Employeeworkcontactreport.html
Employee start date | http://works.devss.net/hrms/Employeestartdate.html
Mandatory documents | http://works.devss.net/hrms/Mandatorydocuments.html
− Performance Reports
Appraisal summary report | http://works.devss.net/hrms/appsummary.html
Performance warnings report | http://works.devss.net/hrms/warningreport.html
− Talent Management Reports
└ Vacancy Succession Report | http://works.devss.net/hrms/succession.html
└ Job Opening Report
└ Candidates Report | http://works.devss.net/hrms/research.html
− Training Reports
Training Reports |  | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/viewTrainingReport?reportId=4
− Time & Attendance Reports
└ Projects Reports |  | view page missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/displayProjectReport/reportId/1?backRequest=1
└ Employee Reports |  | view page missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/displayEmployeeReportCriteria/reportId/2
└ Attendance Summary |  | view page missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/displayAttendanceSummaryReportCriteria?reportId=4
− Reports
└ Leave Balances Entitlements & Usage Report |  | not correct -- reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeaveBalanceReport
└ Leave Percentage Report |  | missing please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeavePercentageReport/reportId/21
− Organizational Reports
Age chart | http://works.devss.net/hrms/Agechart.html
Gender chart | http://works.devss.net/hrms/gender.html
Department chart | http://works.devss.net/hrms/departmentchart.html
Job Title chart | http://works.devss.net/hrms/jobrolechart.html
Location chart | http://works.devss.net/hrms/locationchart.html
Manager chart | http://works.devss.net/hrms/managerchart.html
Job status chart | http://works.devss.net/hrms/jobstatuschart.html
Organizational chart | http://works.devss.net/hrms/view.html
− Financial Reports
Employee costs report
Employee direct deposit details report
Recruitment costs report
● Employees
− Add Employee | http://works.devss.net/hrms/add-employee.html | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/addEmployee
− Employee Profile - List | http://works.devss.net/hrms/employee-list.html | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewEmployeeList/reset/1
- Missing sub page | Personal Details | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewEmployee/empNumber/6
- Missing sub page | Contact Details | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/contactDetails/empNumber/6
- Missing sub page | Emergency Contacts | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewEmergencyContacts/empNumber/6
- Missing sub page | Dependents | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewDependents/empNumber/6
- Missing sub page | Immigration | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewImmigration/empNumber/6
- Missing sub page | Reports To | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewReportToDetails/empNumber/6
- Missing sub page | Qualifications | pleaes add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewQualifications/empNumber/6
- Missing sub page | Memberships | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewMemberships/empNumber/6
- Missing sub page | Job History | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewJobDetails/empNumber/6
- Missing sub page | Salary History | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewSalaryList/empNumber/6
- Missing sub page | Direct Deposit | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewDirectDepositDetails/empNumber/6
− Bulk Mass Update | http://works.devss.net/hrms/bulkupdate.html | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/pim/viewBulkUpdater/reset/1
└ View Assets Equipment Assignment | http://works.devss.net/hrms/assets.html | Add edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/asset/viewAssets/reset/1
− Employee Reports
└ Employee Report | http://works.devss.net/hrms/employeereport.html | fix edit page as per orangehrm
└ Head Count Report | http://works.devss.net/hrms/headcount.html | fix page - fix edit report page as per orangehrm
└ License Expiration Report | http://works.devss.net/hrms/licenseexpiry.html | fix page - fix edit report page as per orangehrm
└ Employee Turnover Hiring Report | http://works.devss.net/hrms/turnoverhiring.html | fix page - fix edit report page as per orangehrm
└ Employee Turnover Termination Report | http://works.devss.net/hrms/turnovertermination.html | fix page - fix edit report page as per orangehrm
● Self Service
− Personal Information
- Personal Details | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewMyDetails
- Contact Details | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/contactDetails/empNumber/20
- Emergency Contacts | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewEmergencyContacts/empNumber/20
- Dependents | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewEmergencyContacts/empNumber/20
- Citizenship Details | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewImmigration/empNumber/20
- Reports To | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewReportToDetails/empNumber/20
- Credentials | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewQualifications/empNumber/20
- Memberships | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewMemberships/empNumber/20
- Job History | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewJobDetails/empNumber/20
- Salary History | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewSalaryList/empNumber/20
− Time Tracking
- Timesheet | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/time/viewMyTimesheet
− Clock In/Out
− Timeoff Requests | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/leave/viewMyLeaveList
− Work Schedule
- Request Schedule Change
− Performance Reviews
└ Appraisals
└ 360 Feedback Peer Reviews
└ Warnings
− Training
└ Training Courses
└ Training Requests
− Benefits
└ Benefit Information
− Payroll
└ Direct Deposit Information | http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/pim/viewDirectDepositDetails/empNumber/20
└ Paychecks
− Props | Kudos
● Manager Self Service
− Time & Attendance
- Timesheet Approval | Timesheets http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/time/viewEmployeeTimesheet
- Leave Request List | My Leave List http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/leave/viewLeaveList
- Time Off Request | Apply Leave http://vmckoy.trial47.orangehrmlive.com/symfony/web/index.php/leave/applyLeave
- Schedule Change Request
● Performance Management
− Manage Trackers Setup Reviewers |  | not correct missing pages reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performanceTracker/addPerformanceTracker
− Employee Trackers Employee Reviewrs |  | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performanceTracker/addPerformanceTrackerLog/trackId/3
− Setup Competencies
└ Competencies y List |  | add edit feature: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performanceTracker/addPerformanceTrackerLog/trackId/3
└ Competencies y Mapping |  | not correct -- add missing Add page -- reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/competencyEmployeeGroups
− Employee Goals
└ Employee Goals |  | not correct - reclone All pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/viewEmployeeGoalList
− Employee Appraisals
└ Employee Appraisals |  | not correct - reclone All pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/viewAllAppraisals
− Configuration Setup Appraisals
└ Appraisals |  | not correct - reclone correctly: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/evaluatorGroupConfig
Missing sub page | Evaluators | add missing page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/evaluatorGroupConfig
Missing sub page | Questions | add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/viewQuestionList
Missing sub page | Form Format | add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/appraisalFormatGlobalConf
Missing sub page | Header Template | add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/performance/viewAppraisalHeaderList
− Reports
- Appraisal summary report
- Performance warnings report
● Talent Management
− Candidates | http://works.devss.net/hrms/candidate.html | not correct please add edit feature on candidate name and reclone page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/addCandidate?id=13
− Vacancies Job Openings |  | not correct -- please reclone ALL features and workflow see Status sub pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/viewJobVacancy
Missing sub page | Edit Vacancy | Please clone ALL features: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/addJobVacancy?vacancyId=2
Missing sub page | Application Form | Please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/viewVacancyFormsListSimple/vacancyId/2
Missing sub page | Best Match Rule | Please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/viewVacancyFormsListSimple/vacancyId/2
− Configuration Setup Questions
└ Question Tags Interview Question Types |  | missing features reclone page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/viewVacancyQuestionTagList
└ Question Pools Interview Questions |  | not correct: please reclone all features: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/recruitment/saveVacancyQuestion
− Reports
└ Vacancy Succession Report
└ Job Opening Report
└ Candidates Report
● Time & Attendance | http://works.devss.net/hrms/timesheet.html
− Timesheets
└ Timesheets | missing comment feature on edit timesheet | not correct please fix: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/editTimesheet?employeeId=5&timesheetId=127&actionName=viewTimesheet
└ Export to CSV Export Timesheets |  | not correct please reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/viewTimesheetCsvExtract
− Attendance
└ Attendance Records |  | not correct - please reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/attendance/viewAttendanceRecord
└ Configuration Setup Time & Attendance |  | page layout - missing buttons not correct - please reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/attendance/configure
└ Export Attendance to CVS |  | Validated
└ Import Attendance Data Upload |  | Validated
− Reports
└ Projects Reports |  | view page missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/displayProjectReport/reportId/1?backRequest=1
└ Employee Reports |  | view page missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/displayEmployeeReportCriteria/reportId/2
└ Attendance Summary |  | view page missing: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/time/displayAttendanceSummaryReportCriteria?reportId=4
− Setup Project
└ Customer |  | Validated perfer edit feature
└ Projects Information |  | not correct reclone http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/admin/saveProject?projectId=3
● Leave Management | http://works.devss.net/hrms/timeoff.html
− Entitlements Leave Balances
└ Entitlement Leave Information |  | not correct - reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/addLeaveEntitlement
└ Employee Entitlements Leave |  | not correct -- reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeaveEntitlements/reset/1
− Leave Approval List Report |  | not correct - reclone all features: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeaveList/reset/1
− Assign Leave Request |  | not correct - reclone add check leave balances: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/assignLeave
− Leave Calendar | http://professional.demo.orangehrmlive.com/symfony/web/index.php/leave/showLeaveCalendar | not correct - clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/showLeaveCalendar
− Reports
└ Leave Balances Entitlements & Usage Report |  | not correct -- reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeaveBalanceReport
└ Leave Percentage Report |  | missing please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeavePercentageReport/reportId/21
− Configure Setup Leave
└ Leave Period |  | not correct -- reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeavePeriod
└ Leave Types |  | not correct -- reclonne: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeaveType and ADD missing pages from Leave Rule: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/leaveTypeList
Missing sub page | Leave Rule - General page | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeaveTypeRule?id=16
Missing sub page | Leave Rule - Who can apply page | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeaveTypeRuleWhoCanApply/id/16
Missing sub page | Leave Rule - Apply/Assign Restrictions page | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeaveTypeRuleApplyRestriction/id/16
Missing sub page | Leave Rule - Accural Rule page | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeaveTypeRuleAccrualRule/id/27
Missing sub page | Leave Rule - Carry Forward Rule page | please add: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineLeaveTypeCarryForwardRule/id/27
└ Work Week |  | add all countries from drop down: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/defineWorkWeek
└ Holidays |  | add all countries from drop down: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewHolidayList
└ Notifications |  | fix fields on the page: the add column too wide: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/leave/viewLeaveNotifications
● Benefits Administration
− Setup Benefits Programs | http://works.devss.net/hrms/bebefits.html -- fix spelling should be benefits
− Setup Benefit Types
− Benefits Enrollment
− Reports
● Schedule Management | please hurry and clone features before 15 day trial expires.
● Payroll USA | please hurry and clone features before 15 day trial expires.
● Training & Development
− Training Administration
└ Packages | http://works.devss.net/hrms/packages.html | not correct reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/viewPackageList
Missing sub page | Package Details | Add missing page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/addPackage
Missing sub page | Add Course | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/addCoursesToPackage/packageId/2
Missing sub page | Students | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/definePackageStudent/packageId/2
└ Courses | http://works.devss.net/hrms/course.html | not correct: reclone all pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/viewCourseList
Missing sub page | Course Details | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/addCourse
Missing sub page | Add Package | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/defineCoursePackage/courseId/3
└ Sessions | http://works.devss.net/hrms/sessiondetails.html | not correct -- reclone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/viewSessionList
Missing sub page | Session Details | Add missing page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/addSession
Missing sub page | Add Trainers | Add missing page: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/defineSessionTrainer/sessionId/2
Missing sub page | Add Students | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/defineSessionStudent/sessionId/2
− Reports
Training Reports |  | Add missing pages: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/training/viewTrainingReport?reportId=4
● Spring Extras
− Calendar | http://works.devss.net/hrms/cal.html
− Directory | http://works.devss.net/hrms/directory.html | please clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/directory/viewDirectory/reset/1
− Organization Chart | http://works.devss.net/hrms/view.html | please clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/orgChart/orgchartView
− Documents | http://works.devss.net/hrms/publishdoc.html | please clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/news/viewDocumentArticle/type/documents/status/published
− News | http://works.devss.net/hrms/publishnews.html | please add & clone: http://varcon.trial45.orangehrmlive.com/symfony/web/index.php/news/viewAnnouncementModule/type/news/status/published
*

## Sheet1
SpringHRM Menu & Pages | Admin | Manager | Employer | Milestone | Start Date | End Date | Estimated End Date | Actual End Date | Developer Feedbacks | Client Feedbacks
● Admin Dashboard | DashBoard Setup page |  |  | Milestone 1 | 2015-02-16 | 2015-02-16
DashBoard display page
Setup Spring Links
Recent Articles
Alerts
Company Directory Search
Workflow
● Manager Dashboard
● Employee (Non Manager) Dashboard
● Spring Admin
− User Management
└ Users | Add / Edit / Delete / Modify Region / Search / Pagination
└ User Roles | Add / Edit / Delete / Search / Pagination
- Setup SpringTools
└ Dashboard Settings
└ Email Settings | Mail Configuration - Add / Edit
└ Email Subscription | Subscriber - Add / Edit / Delete / Subscription List / Search / Pagination
└ Localization
└ Notifications | Add / Edit / Delete / Notifications List / Search / Pagination
└ Open ID | Add / Edit / Delete / Provider List / Search / Pagination
└ Authentication
└ LDAP
- API Settings
− Audit Trail
− Auditing
− Backups
− Delete Account
− Settings
└ Social Settings
└ Social Site Settings
└ Security Settings
− Manage My Account
● Core HR
− Setup Org Data
└ General Information
└ Location
└ Department Structure
└ Reporting Method
└ Define Setup Hierarchy
└ View Org Chart
− Setup CoreHR
└ Optional Fields
└ Custom Fields
└ Data Import
└ Termination Reasons
− Setup Job Data
└ Job Titles
└ Salary Components
└ Pay Grades
└ Employment Status
└ Job Categories
└ Work Shifts
− Setup Credentials
└ Skills
└ Licenses
└ Education
└ Languages
└ Memberships
− Setup Nationalities
− Setup News & Documents
└ News
└ News Categories
└ Documents
└ Document Categories
└ Events
− Set up Onboarding
└ Task Types
└ Events
− Assets Setup Equipment
└ Asset Brand Information
└ Asset Categories
└ View Assets Equipment Assignment
└ Vendors
● HR Reports
− Onboarding Reports
└ Event Progress
└ Participant Progress
− Employee Reports
└ Employee Report
└ Head Count Report
└ License Expiration Report
└ Employee Turnover Hiring Report
└ Employee Turnover Termination Report
Employee diversity report
Employee custom fields
└ Employee Date of Birth
└ Employee Employees hired for each location
└ Employee Employees hired for each sub-unit
└ Employee Employees over 20 years
└ Employee Employment Status of Employees
└ Female Employee List with Service period over 1 year
└ Employee Joined Date between 2010 - 2012
└ Employee Marital Status
└ Employee PIM data verification
└ Employee PIM Sample Report
└ Employee Supervisor Subordinate Details
− Management Reports
Employee job history report
New hires report
Employee Termination date
Employee list report
Employee contact list report
Employee emergency contact report
Employee timesheet report
Employee length of service report
Employee work contact report
Employee start date
Mandatory documents
− Performance Reports
- Appraisal summary report
Review and Appraisal Progress report
Performance Comparison Report
Employee Performance Profile
Performance Progress
Performance warnings report
− Talent Management Reports
└ Vacancy Succession Report
└ Job Opening Report
└ Candidates Report
− Training Reports
Training Reports
− Time & Attendance Reports
└ Projects Reports
└ Employee Reports
└ Attendance Summary
└Monthly Attendance Summary
− Leave Reports
└ Leave Balances & Usage Report
└ Leave Percentage Report
− Organizational Reports
Age chart
Gender chart
Department chart
Job Title chart
Location chart
Manager chart
Job status chart
Organizational chart
− Financial Reports
Employee costs report
Employee direct deposit details report
Recruitment costs report
- Benefits Reports
- Scheduling Reports
- Payroll Reports
● Employees
− Add Employee
− Employee Profile
- Missing Benefits sub page
- Missing Pay Details sub page(s)
− Bulk Mass Update
└ View Assets Equipment Assignment
− Employee Reports
└ Employee Report
└ Head Count Report
└ License Expiration Report
└ Employee Turnover Hiring Report
└ Employee Turnover Termination Report
● Self Service
− Personal Information
- Personal Details
- Contact Details
- Emergency Contacts
- Benefits
- View Medical Insurance Details
- Dependents
- Citizenship Details
- Reports To
- Credentials
- Memberships
- Job History
- Salary History
- Direct Deposit
− Time & Attendance
- Timesheet
− Punch In/Out
− Attendance
− Leave Information
− Request Leave
− Request Leave Status
− Leave Balances
− My Leave Balance and Usage Report
− Time Off Calendar
− Work Schedule
− My Work Schedule - Design Pending
− My Team Schedule - Design Pending
− Work Schedule Request - Design Pending
− Other Feature - Design Pending
− Performance Reviews
└ My Peer Reviewers
└ My Warnings
└ Peer Reviews
└ My Goals
└ My Appraisals
− Training & Development
└ Training Sessions
└ My Training
− Payroll Information
└ My Paycheck Details
└ My Federal & Tax Details
└ View Pay Card
− My Onboarding Tasks
− My Company Equipment
└ My Equipment
− Give Props
− My Props
● Manager Self Service
- My Organization
- My Reports To
- Employee List
- My Onboarding Tasks
−Time & Attendance
- Employee Timesheet
- View Employee Attendance
- Leave Management
- Leave List
− Employee Leave Balance
− Assign Leave
− Leave Calendar
- Performance Management
− Peer Reviewers List
− Employee Goals
− Employee Appraisals
- Talent Management
− Candidates
- Job Openings
- Schedule Interview
- Schedule Management
- Employee Schedules - Design Pending
- Employee Schedules Request - Design Pending
- Other Features - Design Pending
− Manager Reports
Employee job history report
New hires report
Employee Termination date
Employee list report
Employee contact list report
Employee emergency contact report
Employee timesheet report
Employee length of service report
Employee work contact report
Employee start date
Mandatory documents
- Appraisal summary report
- Review and Appraisal Progress Report
- Performance Comparison Report
- Employee Performance Profile
- Performance Progress
Performance warnings report
Training Reports
Attendance Summary
└Monthly Attendance Summary
Leave Balances & Usage Report
Leave Percentage Report
● Discipline
- Discipline Cases
− Configuration
└ Disciplinary Document Templates
● Performance Management
- Setup Peer Reviewers
− Peer Reviewers List
− Setup Competencies
└ Competencies
└ Competencies Mapping
− Employee Goals
└ Employee Goals
− Employee Appraisals
└ Employee Appraisals
− Setup Appraisals
└ Appraisals
− Reports
- Appraisal summary report
Review and Appraisal Progress report
Performance Comparison Report
Employee Performance Profile
Performance Progress
- Performance warnings report
● Talent Management
− Candidates
− Schedule Interview
− Job Openings
− Setup Questions
└ Interview Question Types
└ Interview Questions
− Setup Social Recruitment
- Setup RSS Feed URL
- Setup Webpage URL
− Reports
└ Vacancy Succession Report
└ Job Opening Report
└ Candidates Report
● Time & Attendance
− Timesheets
└ Employee Timesheets
└ Export Timesheets
− Attendance
└ Attendance
└ Setup Time & Attendance
└ Export Attendance
└ Import Attendance
− Reports
└ Projects Reports
└ Employee Reports
└ Attendance Summary
└Monthly Attendance Summary
− Setup Project
└ Customer
└ Projects Information
● Leave Management
− Leave Balances
└ Leave Information
└ Employee Leave
− Leave Approval Report
− Leave Request
− Leave Calendar
− Reports
└ Leave Balances & Usage Report
└ Leave Percentage Report
− Setup Leave
└ Leave Period
└ Leave Types
└ Work Week
└ Holidays
└ Notifications
● Benefits Administration
− Setup Benefits - Design Pending
− Maintain Employee Benefits - Design Pending
− Benefit Reports
● Schedule Management
− Setup Schedule Management - Design Pending
− Maintain Employee Schedules - Design Pending
− Other Features - Design Pending
− Schedule Reports - Design Pending
● Payroll USA
− Setup Payroll - Design Pending
− Maintain Employee Payroll - Design Pending
− Payroll Processing - Design Pending
− Payroll Reports - Design Pending
- Pay Card Setup
● Training & Development
− Training Administration
└ Packages
└ Courses
└ Sessions
− Reports
Training Reports
● Spring Extras
− Calendar
− Directory
− Organization Chart
− Documents
− News
− Events
● Change Password - Top Right
● Edit Profile - Top Right
● Localization - Top Right